## Dashboard
Portfolio Executive Dashboard
| Submission Deadline | 2026-05-31 | Weekly Target Hours | 12 | Plato Target | 6 | Prototype Target | 4 | Review Target | 1 | Buffer Target | 1
| Planned Weeks | 6 | Hours Logged | 0 | % of Plan | 0% | Days to Deadline | -14 | Prototype Avg % | 0% | Tasks Due This Week | 0
Week | Start | End | Plato Hrs | Prototype Hrs | Review Hrs | Buffer Hrs | Total Hrs | % of Target | Key Deliverable | Status | Hours Flag | Week Notes | Week | Actual Hrs | Target Hrs
Week 1 | 2026-04-20 | 2026-04-26 |  |  |  |  | 0 | 0% | Finalize scenario narrative | Not Started | At Risk |  | Week 1 | 0 | 12
Week 2 | 2026-04-27 | 2026-05-03 |  |  |  |  | 0 | 0% | Map branching decisions | Not Started | At Risk |  | Week 2 | 0 | 12
Week 3 | 2026-05-04 | 2026-05-10 |  |  |  |  | 0 | 0% | Draft legal + trauma-informed guardrails | Not Started | At Risk |  | Week 3 | 0 | 12
Week 4 | 2026-05-11 | 2026-05-17 |  |  |  |  | 0 | 0% | Build working interaction | Not Started | At Risk |  | Week 4 | 0 | 12
Week 5 | 2026-05-18 | 2026-05-24 |  |  |  |  | 0 | 0% | Capture screenshots / visuals | Not Started | At Risk |  | Week 5 | 0 | 12
Week 6 | 2026-05-25 | 2026-05-31 |  |  |  |  | 0 | 0% | Assemble + polish final portfolio | Not Started | At Risk |  | Week 6 | 0 | 12
Tip: Enter actual hours each week in blue cells D:G. Status has a dropdown.

## Tasks
Master Task Tracker
ID | Task | Domain | Impact (1-3) | Urgency (1-3) | Effort (1-3) | Priority Score | Due Date | Week | Status | Next Action | Notes
P-01 | Finish Plato lesson artifacts | Plato | 3 | 3 | 2 | 10 | 2026-04-26 | Week 1 | In Progress | Complete current lesson and save artifact
PR-01 | Write full scenario narrative | Prototype | 3 | 2 | 2 | 8 | 2026-04-26 | Week 1 | Next Up | Draft final version for portfolio
PR-02 | Map branching decisions | Prototype | 3 | 3 | 3 | 9 | 2026-05-03 | Week 2 | Not Started | Create branch map
L-01 | Complete weekly Liberty coursework | Liberty | 3 | 3 | 2 | 10 | 2026-04-26 | Week 1 | Not Started | Reserve Sunday block
Scoring note: | Priority Score = (Impact × 2) + (Urgency × 2) – Effort. Higher score = do sooner.

## Prototype Roadmap
Prototype Roadmap + Prompt Experiment Log
Milestone | Owner | Target Date | % Complete | Status | Notes | Portfolio Asset?
Scenario narrative | Me | 2026-04-26 | 0% | Not Started | Lock final story details | Yes
Decision branches | Me | 2026-05-03 | 0% | Not Started | Map educator choices and consequences | Yes
Legal guardrails | Me | 2026-05-10 | 0% | Not Started | Build compliant reporting guidance | Yes
Trauma-informed prompts | Me | 2026-05-10 | 0% | Not Started | Draft learner-safe responses | Yes
Working demo | Me | 2026-05-17 | 0% | Not Started | Small isolated prototype | Yes
Portfolio screenshots | Me | 2026-05-24 | 0% | Not Started | Capture visuals and captions | Yes
Prompt Engineering Experiment Log
Experiment ID | Date | Goal | Prompt / Variation Tested | What I Learned | Keep / Drop / Revise | Next Test

## Pulse Check
Weekly Pulse Check
Use this tab every Sunday or Monday. Keep answers short and honest.
Week | Hours Target | Hours Actual | Did 12 Happen? | Did Prototype Move? | Biggest Blocker | What Helped | Top 3 Next Week | Adjustment
Week 1 | 12 | 0 | No
Week 2 | 12 | 0 | No
Week 3 | 12 | 0 | No
Week 4 | 12 | 0 | No
Week 5 | 12 | 0 | No
Week 6 | 12 | 0 | No
Prompt Bank
• Did the 12 hours happen? If not, how many did happen?
• Did the prototype move forward in a meaningful way?
• What created friction this week?
• What is due next week?
• What should get my best hours first?

## Impact Dashboard
KPI Name | How I'll Measure It (Method) | Baseline / Target for August | Current Status
Functional Prototype Completion | Milestone checklist: scenario written, branching logic built, prompts tested, visuals added, demo ready | 100% complete for one module | Not yet measured
Expert / Stakeholder Feedback Volume | Count structured demos, calls, or reviews with educators/admins/counselors/legal stakeholders | 5 completed feedback conversations | Not yet measured
Prototype Quality & Readiness | Track revisions, usability notes, and whether user can complete scenario independently | 3 rounds of iteration + demo ready | Not yet measured
Collaboration / Pilot Pipeline | Count qualified leads interested in advising, piloting, or backing project | 2 warm leads | Not yet measured